EVENT MANAGEMENT PLAN – UPDATED February 2025

Further to discussions and helpful provision of sample documentation from David Catterall at Bury and Nick Moore at Newcastle-under-Lyme, there is now added template info at the bottom of the original Market Place document. Many thanks to David and Nick for further information to support colleagues.

The original document, helpfully provided by Market Place (Europe) – a sponsor of NABMA – provides a good awareness example for those market managers considering a specialist event and requiring a template for amending to cope with local circumstances

1. Introduction

xxx has been licensed to organise a market in xxxx.

Pre-event discussions have taken place between xxx and the organiser of the Festival and the following Event Management Plan has been prepared in accordance with the instructions arising from those discussions and will incorporate any further conditions required for use of the venue.

The Markets will feature quality market traders selling an array of foods and products.

A detailed breakdown of the traders’ names, country of origin and products on sale will be given prior to the event.

2. Management

xxx will ensure that at least one of the senior managers/authorised personnel will be on site throughout the duration of the event and it is anticipated that the personnel in attendance for the Market will be as follows:-

| NAME | POSITION | PERIOD OF DUTY | CONTACT DETAILS |
| --- | --- | --- | --- |

xxx reserve the right to alter the above in cases of unforeseen and/or emergency situations and in such instances the alteration will be notified to the Events Team.

Xxx Senior managers will be in attendance on site no later than xx am on the xx of the event for the purpose of ‘marking out’ and any alterations to the previously agreed site dimensions or any conditions attached to the site itself must be notified to xx before ‘marking out’ commences.

The Senior Management Team are very experienced in the organisation and operation of Markets and have developed an effective system of communicating directions, advice and information to the traders and although the relevant officers of xxx can, of course, approach the traders at any time should the need arise, it would be greatly appreciated if such contact could be made directly through the senior manager present.

xxx will not have a fixed, on-site office at the event but at all times for the duration of the event the xxx personnel on-site will be able to be contacted either in person or by mobile phone, the numbers are shown in the management team assigned to this contract above.

3. Site Logistics

Location

The Market will be held in the following locations:-

Layout

The layout proposals are detailed in a plan appended to this Management Plan. The location of the stalls within the Market will be configured in such a way to ensure that all fire hydrants remain unobstructed and that a 4mtr Emergency corridor is maintained throughout the site. All access to all specified safety and/or security access/egress points; all nominated through walkways will be maintained at all times to promote good customer flow throughout the site.  Encroachment into unauthorised areas will not be permitted and every reasonable attempt will be made to ensure that the Market will contribute significantly to the ambiance of the street environment and compliment the existing retail offer without creating any pinch points or areas of congestion.

At all times xxx will take every reasonable step to ensure that the layout of the market is such that bottlenecks, “pinch points” and areas of excessive pedestrian conflict, both within the Market and in neighbouring areas, are eliminated wherever they occur and the on-site xxx manager will take immediate steps to address any crowd control problems if they were to arise.

Set up Times

The set up and take down times for this event will be:-

| Day(s) | Set Up / Restocking Times | De Rig / Restocking Times |
| --- | --- | --- |
| Friday | Marking out of site 2-8.00 |  |
| Saturday | 06.00-09.30 |  |
| Sunday | 06.00 to 09.30 | 6pm to 9pm |

All vehicles to be removed from site by 9.30am Saturday and Sunday

xxx may, further to consultation with the event coordinator, amend the traders setting up and/or taking down times accordingly.

The Market once erected remains in situ for the duration of the event and overnight security will guard the market outside of operational hours.

Trading Hours

| Days | Trading Hours |
| --- | --- |
| Saturday | 10.30-17.00. |
| Sunday | 10.30-17.00 |

Stalls will be required to be opened for business during all hours of the event.

Stalls

In all cases traders will supply, erect, dismantle and service their own stalls.  All stalls are of a high quality, attractive appearance and are mainly of the umbrella style or Pop up Mini Marquee style of construction.  All stall coverings are Fire rated to BS 7837. The safe working requirements of these types of stall are detailed in the relevant section of the Event Risk Assessment below.  As a general rule, vehicles are not allowed to remain on site behind stalls once setting up is complete.  However, there may be some specially modified vehicles and/or trailers which have been customized into bespoke trading units and such units will be allowed to remain on site provided that they are being used as trading units.

Traffic and vehicular management

Market vehicles will be restricted to 5 M.P.H. at all times whilst within the market site.

Vehicular access is restricted to before 09.30 and from 18.00 to 10:00pm every day.

Due to the fact that the designated event site is such a busy pedestrian area special measures will be implemented to ensure that all vehicles entering xxx will have Banksmen to guide them through to the nearest position to their stall location. Where necessary, barriers will be put up to keep members of the public away from any work areas. The early set up and the late break down and restocking times significantly reduces the potential pedestrian conflict with event related vehicles outside of the initial Build and De-Construction phases.

Given the number of trader’s vehicles being permitted on site, the management personnel will pay particular attention to incremental and orderly access and egress of trader’s vehicles and at such times all xxx personnel will wear yellow, high visibility jackets to assist in the safe movement off and on of traders vehicles.

The intention to leave the market stalls in situ once erected will reduce the length of time vehicles will be required on site and will therefore reduce vehicular movement significantly.

The proposed layout recognizes the need to turn vehicles in order that reversing of vehicles is kept to a minimum.

Notwithstanding the above, xxx personnel will be on site at all times and will pay particular attention to ensure that all traders comply with the traffic management requirements.

All traders are required to make their own off-site parking arrangements.

Electricity supply

xxx have agreed that xxx will use xxx to supply all the necessary dedicated Generators and distribution Boards.

It has also been agreed that xxx will provide the services of a qualified electrical engineer to ensure the safe connection of each distribution board to ensure maximum efficiency in the provision of power to each area required.

xxx together with their nominated Electrical contractor will also oversee the safe and secure setting up of the power supplies to each stall, including the safe positioning of the power cables, and to ensure that the electrical installations to and within the stalls are also safe and secure.

It is a requirement of attendance at the event that all traders must have all portable electrical equipment and appliances tested at least once each year and that all copy certificates must be made available on request by the traders. Copy PA Test certificates for traders electrical equipment are held by xxx and can be made available if required.

L.P.G.

The use of L.P.G. is generally discouraged on the Market although there is a limited need from some of the specialist hot food traders to use L.P.G. in respect of their on site cooking activities.

The use of L.P.G. is restricted to one bottle and one spare only at any one time allowed on the stall. No additional gas bottles are permitted to be stored on site at any time. All traders will carry the Gas Safe Certification for each appliance.

Fire Fighting Equipment

Every trader involved in any type of cooking operation is required to carry the necessary fire fighting equipment on the stall at all times.

Each piece of firefighting equipment is required to be checked annually and the trader required to maintain copies of all paperwork showing the annual inspection details on the stall for inspection when requested.

Water

A potable water supply will be made available by xxx by 4 stand pipes situated at the areas shown on the attached plan.

Refuse removal

The event organiser will organise refuse contractors for the collection, separation and removal of all waste materials from the Market in accordance with the company’s commitment to recycling initiatives.

Furthermore traders will be required to maintain and keep clean both their stall area and the areas immediately adjacent throughout the day at all times.

Security

xxx management will act as on site stewards during the course of each event. The overnight security for each event will be provided by the event organiser.

Site Evacuation

The site specific evacuation planning requirements for the event will depend to a large extent upon the overall Evacuation Plan for xxx and the nature of any incident requiring the evacuation of the market. Upon receipt of such a plan from the responsible officer, the generic evacuation plan for the Market will be amended as appropriate.

Managers and Traders will also be made aware of their role and responsibility in assisting members of the public where necessary.

The exact position and size of each stall will be clearly marked out as detailed above on the day before each event and xxx would welcome the attendance of the responsible Officer of xxx to ensure that sufficient avenues for evacuation are catered for.

4. Health and Safety

xxx recognises and accepts its responsibility as a high quality event market operator for providing a safe and healthy working environment for all of its traders and their employees and for the provision of a safe and healthy environment for all members of the public attending the Market.

In taking all reasonable, practicable steps to meet this responsibility, xxx give particular attention to the provision and maintenance of:-

- Safe plant, equipment and systems of work.

- Safe arrangements for the use, handling and storage of substances.

- A safe place of work and safe access in and around the Market.

- A healthy working and shopping environment.

- Adequate health and safety facilities.

- Sufficient information, instruction, advice and supervision to enable all users of the Market to avoid hazards and to contribute positively to the overall safety of the event.

No safety policy is likely to be successful if it is operated in isolation.  Xxx will therefore fully co-operate with the Councils’ Health and Safety Officer and provide them where necessary with sufficient information and assistance in order to ensure the safety of the event.

Although on-site personnel will be responsible for the implementation and maintenance of the Health and Safety policy, including where necessary the on-site modification of any risk assessments or other matters, xxx will also call upon the services and expertise of a Health and Safety advisor.

A full copy of xxx Health and Safety Policy and the Risk Assessments covering all aspect of the Market are attached as an appendix to the Event Management Plan.

5. Food Hygiene, Food Safety and Trading Standards

Prior to the commencement of each market, the responsible officer of the Council will be provided with a full breakdown of the traders in attendance  detailing  their name, country of origin and the goods to be sold.  In the unlikely event of the Council having any concerns or reservations about any of the traders or the goods to be sold, it would be greatly appreciated if xxx could be informed of such concerns as soon as possible.

A copy of the LACORS guide has been issued to all traders who attend any Market operated by xxx. Traders are kept fully up to date with any and all new legal requirements which may be applicable to Markets and to advise them on any and all revisions or modifications to existing requirements.

In order to avoid any misunderstandings and to ensure that all aspect of the Market meet all legal and local requirements, xxx actively encourages and welcomes inspections by the relevant officers from the Councils Health and Safety, Environmental Trading Standards Departments both before and during the event at any time.  To this end it is strongly recommended that an on-site meeting be held with all relevant personnel at a time and place to be agreed in the mid-morning period of the first day of each event.  The Councils responsible officer will be responsible for organizing the meeting.

6. Insurances

xxx carry full Operators Public Liability Insurance cover for up to £5,000,000 for any one claim and a copy of the Insurance Certificate is enclosed.  Further more detailed information in respect of xxx insurance cover can be provided on request.

In addition all traders are required to carry up to £5,000,000 Traders Public Liability Insurance cover.

EVENT MANAGEMENT PLAN

As an Event Organiser you are responsible for:

- Informing Bury Council Event Safety Advisory Group of your event

- Seeking permission of the relevant landowner

- Submitting the relevant documentation to the Bury Event Safety Advisory Group in a timely manner to ensure it can be reviewed

- Submitting road closure requests a minimum of 12 weeks before your event (please contact traffic@bury.gov.uk)

- Ensuring the overall safety at your event as far as reasonably practicable

- Ensuring that health and safety arrangements are in place to control risks

- Ensuring the competence of staff at your event to undertake their roles safely

- Checking all insurance documents, risk assessments and methods of work for contractors, stall holders, caterers etc.

- The Health, Safety and Welfare of all members of staff, contractors and members of the public attending your event

- Informing the Performing Rights Society if you have live music at your event

Disclaimer: This template is a guide only. It does not necessarily include all the information that may be relevant to your event. Bury Council Event Safety Advisory Group are not responsible for any lack of information not submitted with this application.

Privacy Statement

Your personal information is required for administration purposes. Bury Council are committed to protecting your privacy and fulfilling its obligations under UK data protection laws. Bury Council may use this data in order to inform you of its activities and/or improve its services in relation to the subject matter only, but will not sell, rent, distribute or otherwise make your data commercially available to any third party, unless it is required to by a court order or to comply with other legal requirements.

What happens to my event information?

Your event management plan, site plan, risk assessment and public liability certificate will be sent to the Safety Advisory Group (SAG) for review. The SAG consists of representatives from various departments at Bury Council, Greater Manchester Fire and Rescue, Greater Manchester Police, North-west Ambulance Service and other relevant parties. Your information will not be passed on to any other party without your prior consent.

Contents

1. Event Overview

2. Site Management

3. Incident Management

4. Traffic Management Plan

5. Event Safety Measures

Please type your answers into the white boxes

Event Organiser Details

| Event Organiser Name | David Catterall / Victoria Robinson / Jennifer Smith |
| --- | --- |
| Organisation | Bury BID, Bury Market, Broadstreet Social and The Met Theatre |
| Contact Telephone Number | 0161 253 7064 |
| Email Address | d.catterall@bury.gov.uk |
| Name of Event | Bury Food and Drink Festival |
| Location of Event | Bury Market, Millgate Square and Kay Gardens |
| Date of Event | Thursday 23rd May – 5.00pm – 10.00pm Friday 24th and Saturday 25th May 9am – 5pm |
| Contact Telephone Number on day of the event (if different to above) | 07739016893 |

1. 	Event Overview

1.1	Event Overview

Please provide a description of your event

A variety of food and drink stalls located across the locations stated above. Please note, there will be no alcohol provision within Kay Gardens

| Please provide the following information about your event |  |
| --- | --- |
| Event start time | Thursday 23rd May – 5.00pm – 10.00pm Friday 24th and Saturday 25th May 9am – 5pm |
| Event end time |  |
| Expected number of attendees | 350-500 Thursday 1500 per day Friday and Saturday |

1.2	Event Itinerary

| Please provide timings of your event including set up and break down timings |  |
| --- | --- |
| Date / Time | Action |
| Thursday 23rd / 4.30pm | Set up of gazebos on the Golden Mile |
| 5.00pm | Event starts |
| 9.00pm | Event ends, market team break down stalls and gazebos |
| Friday 24th May / 8am Friday 24th May / 5pm | Normal Market Set up with the market team. Food vans to set up in Kay Gardens with support from the market team. Break down with the market team. |
| Saturday 25th May / 8am Saturday 25th May / 5pm | Normal Market Set up with the market team. Food vans to set up in Kay Gardens with support from the market team. Break down with the market team. |

1.3	Programme of Events

| Please provide your programme of activities and the timings for the day, including any performances (e.g. the start and finish times of any musical performances) |  |
| --- | --- |
| Time | Activity |
| 6pm – 9pm | Thursday 23rd May - Late night food market in The Mill Gate shopping centre and Market Square - Music and food in and around the bars in Bury. |
| 9am – 5pm | Friday 24th May - Bury Beer Festival – Derby Hall, The Met – paid ticket event. - Music and food and drink across bars in Bury. - Pop up market in Millgate square |
| 9am – 5pm | Saturday 25th May - Pop up food market in Market Square to highlight Bury Market’s food offer. - Music and food and drink across bars in Bury (details tbc) |

1.4	Event Management

Roles and Responsibilities on Event Day (s)

| Please provide a brief description of the roles of event staff and their main responsibilities. There may be other roles that are not listed here that are applicable to your event. Please note: the role of stewards is covered in section 2.13 so there is no need to complete the role of stewards in this section |  |
| --- | --- |
| Role | Responsibilities |
| Event Organiser | David Catterall and Victoria Robinson - To ensure the safety of the event as well as coordinate the different areas to ensure the event runs smoothly. Responsible for the safety of people attending and those involved in the event. |
| Event Manager | Foundation Events – Scott Richardson – To manage security |
| Site Manager | Market Management Team |
| Health & Safety Officer | Market Management Team |
| Arena/stage Manager | Roch Valley Radio |
| Steward Coordinator | N/A |
| Press and PR coordinator | David Catterall |
| Other | Market Management Team, Scott Richardson, The Met Team – Safeguarding |

1.5	Crowd Management

Please provide details on how you will manage the crowd at your event Please note: the role of stewards is covered in section 2.13 so there is no need to complete the role of stewards in this section

Is your event ticketed? If yes, what arrangements are in place for this?

Expression of interest for those attending. No tickets and it is a free event. Numbers attending will be monitored throughout the day by Scott Richardson, David Catterall and the security team.

How will you manage capacity at your event?

As above

How will you manage the access and egress of the crowd?

We will have stewards at each access and exit point. They will monitor the numbers attending. All stewards will be in contact with each other via personal radios.

1.6	Advertising

Please provide details of how you will advertise your event

How and where do you plan to advertise your event?

Social Media, Radio interviews, Bury Council Comms.

Will the media be in attendance and if so how will you handle them?

We have media partners who will work with the management team to ensure they are operating safely and within the guidelines set.

2.	Site Management

2.1	Contractor Management

| Please provide details of any contractors that will be involved with your event Please ensure that you check any safety documentation of contractors that you hire |  |
| --- | --- |
| Company | What are they providing/doing? |
| Foundation Events | Risk Assessments, Stewards, Radios, high vis outfits, staff management, security |
| Market Management Team | Risk Assessments for all stalls |

2.2	Traders

| Please provide details of any traders/commercial traders and charity stalls that will be at your event Please ensure that you check any safety documentation of traders |  |
| --- | --- |
| Name of Organisation | Concession Type |
| To follow | Food stalls |

Sale of Alcohol If you are selling alcohol at your event please contact the licensing department at Bury Council (licensing@bury.gov.uk) as you will require a temporary events notice. Please explain below how you will manage the sale of alcohol.

The Temporary event notice has been submitted by the Woodcock group, who are providing the bar provision in the Market only. The bar provision will be inside the Market Square. Alcohol will not be permitted in Kay Gardens.

Catering Requirements (Food, drink, water) For each catering supplier/food stall that you have attending your event, please provide the following information: - Name of Business - Address of Business - Contact telephone number - Name of local authority that they are registered with - National food hygiene rating (if available)

To Follow

2.3	Fencing and/or barriers

Please tell us if you plan to use any fencing and or barriers at your event including the type and their location Please ensure that you check any safety documentation of contractors that you hire.

No barriers are required.

2.4	Electricity, Water, Gas Supply and Generators

Please tell us if you plan to use electricity, water, gas supply or other flammable liquids at your event. If so, please tell us where these will be sourced and the processes in place to manage these. Please tell us if you plan to use any generators at your event. If so, please tell us where these will be sourced and the processes in place to manage these, including the storage and management of fuel and other flammable liquids. Please ensure that you check any safety documentation of contractors that you hire.

Power being supplied by Bury Market or independently by the traders.

2.5	Temporary Structures

Please list any temporary structures that you will have at your event and where they will be located e.g. gazebos, marquees, staging Please ensure that you check any safety documentation of contractors that you hire.

Several Gazebos provided by Bury Market. The market risk assessments for the gazebos will be used and reviewed by David Catterall and the Bury Market Management Team.

2.6	Fire Safety

Please ensure that you have considered aspects related to fire safety at your event and provide detail here. Please ensure that you check any safety documentation of contractors that you hire.

Externally, all staging and PA areas will have Fire RAs in place. Fire Marshalls will be appointed. Separate Fire Risk assessment has been submitted to ESAG.

2.7	Temporary Event Notice

IMPORTANT NOTE: Licensable activities at your event such as the sale and supply of alcohol, the provision of late-night refreshments to the public and regulated entertainment may require a temporary event notice (TEN). A temporary event notice is a notification to the licensing authority that an individual intends to carry on licensable activities for a period not exceeding 168 hours. A temporary event notice application must be sent to the licensing authority and the police at least 10 working days in advance of a planned event (not counting the day the notice is given or the day of the event) . Please ensure that you have the necessary licences in place. Please contact your local licensing department for more information.

2.8	Musical Entertainment

Please tell us what entertainment you have arranged for your event i.e. Live music with amplification and how you manage noise disturbance and potential complaints. Important notes: - If you have live music you may require a Temporary Events Notice. - It is your responsibility to inform the Performing Rights Society (www.prsformusic.com) if you are having live music at your event. - Please ensure that you check any safety documentation of contractors that you hire.

The TEN has already been submitted. The current music licence covers the broadcast of music via Roach Valley Radio.

2.9	Attractions

| Please provide details of any attractions that will be at your event e.g. inflatable’s, funfair/children’s rides, fireworks For these attractions make sure that you see a copy of the provider’s public liability insurance, risk assessment and method statement. For rides we will also need the name of each ride and their corresponding ADIPS number (Amusement Device Inspection Protection Scheme) Please ensure that you check any safety documentation of contractors that you hire. |  |
| --- | --- |
| Name, address and telephone number of organisation | Attraction and ADIPS number if applicable |
| TBC |  |

2.10	Medical and First Aid Cover

Please provide details of the medical provider and resources that you have arranged to be at your event including their location (i.e. number of first aiders, doctors, ambulances etc.)

All event staff through Foundation events are first aid trained. First Aid Cover provided by Bury Market Management Team

2.11	Public Health and Welfare

Please provide details of the arrangements you have made for the following:

Toilet Facilities Please provide details of sanitary arrangements, including: number, ratio of male to female and disabled, location, maintenance. Please bear in mind the opening times of public facilities. If inadequate provisions are available this can lead to a risk of a disruption to public order and safety.

Toilet facilities within the market, Millgate and Rock. Additional toilets will be provided.

Waste Disposal Please provide details of the arrangements made for waste disposal, rubbish bins and litter collection at your event. As the event organiser you are responsible for arranging the disposal of waste. Any trade waste must be removed by a registered trade waste contractor. Bury Council is NOT responsible for arranging waste disposal at your event.

0161 253 5353 (Bury Council Waste Management) Daniela Dixon has been contacted and additional waste removal is confirmed as well as street cleansing post the event.

2.12	Accessibility

Please tell us how you have made your event accessible and provide details here. e.g. Accessible toilets provided, Accessible parking, Ramped access, Accessible transport.

The area is fully accessible.

2.13	Steward and Marshal Management

Please provide details of the arrangements you have made for stewards at your event

What are the roles and responsibilities of your stewards?

Foundation Events will manage all stewards. They will support event security throughout the day and supervised by David Catterall, Bury Market Management Team and Scott Richardson

Where will they be positioned and why?

They will be located within Kay Gardens, Peel Statue and Haymarket

Who are your stewards? How will they be identified? We do not require names, just where you have recruited them from.

All stewards will be dressed in uniform and wearing High Viz vests. All Stewards are paid by Foundation Events.

Will you be using Security Industry Authority (SIA) qualified security staff? If so, what will their role be?

Yes, as above.

How will your stewards be trained?

As above

When will your stewards be briefed? Please provide a copy of the information that will be given to Stewards (briefing document)

All stewards will be briefed in the morning of the event. They will also ensure that RAs are reviewed on the day to ensure nothing has changed since they were submitted.

How will the event team and the stewards (including traffic stewards) communicate with each other on the day of the event?

Everyone will have 2-way radios linked into the town centre radio frequency as well as a dedicated channel.

3.	Incident Management

IMPORTANT NOTE: Do not assume that the emergency services will attend your event other than in an emergency. Your event must be managed without the support of the emergency services, even if they have agreed to attend as they may be called away to an emergency elsewhere. Do not refer to support from emergency services throughout this document. They cannot provide support to any element of your event other than in an emergency and even in this instance their first port of call would be your contingency plans.

3.1	Welfare of Children

Please provide details of how you would deal with a lost or found child or vulnerable person at your event. Please include the following: What is your procedure? Who is the designated person in charge of this? Where is the rendezvous point? How will announcements be made?

The market Management team has a process in place for lost children and vulnerable people. The market office located on Princess parade has a reception area for waiting.

3.2	Incident Reporting and Investigation

Please provide details of the system you have in place for reporting and recording accidents and incidents at your event

Incidents and accidents are reportable to Foundation events and reviewed by the Lead organiser and the market management team

3.3	Emergency Plans

IMPORTANT NOTE: It is not the responsibility of the Event Manager/Organiser to run an emergency procedure. If an emergency is to be declared, then operational command will fall to the emergency services. However, procedures need to be in place so that emergencies can be dealt with responsibly until the emergency services arrive. It is important that you set out your procedures carefully and brief all event staff, contractors and volunteers so that they are clear and widely understood. In this situation we would advise that the decision is clearly recorded, including who took it, what time it was taken, and why it was taken.

Please provide details of your emergency plan for the event

It is your responsibility under Health and Safety, and the practice of a Risk Assessment, to consider the ‘what if’s’ at your event (i.e. contingency planning). What are your contingency plans for situations, such as: Need for evacuation, fire, power failure, collapse of a temporary structure, road traffic collision, medical emergency, fatality, adverse weather conditions, key location becomes unavailable, cancellation prior to or during? This is not an exhaustive list and the specific nature of your event will suggest others.

Power failure – Event stalls will continue outside; all indoor and stage activities will cease. Evacuation – See plan below. Collapse of a temp structure – Contact emergency services, cease all activities, evacuate to Whitehead Gardens. End the event. Road Traffic collision – Contact Emergency Services, cease activities in the area. Medical emergency – Request first response from the medical team and contact the Ambulance service. Fatality – Call emergency services, contact GMP onsite, cease all activities, end the event, ensure people leave via exits Adverse Weather condition – End all outdoor activities, monitor indoor footfall, cease all activities if the weather impacts heavily.

At your event, who will be responsible for determining that an incident is now a major incident or emergency and will take responsibility for decisions until the emergency services arrive and take control?

David Catterall, market management team and Scott Richardson

Who will report this to the emergency services?

The first responder

What systems do you have in place to contact the local emergency services?

All stewards have personal mobile phones, and all stewards are in contact using 2 way radios. In attendance are GMP and GMFRS

Who will liaise with the emergency services when they get to the site?

Market Management Team and Scott Richardson

What entrance/access point should the emergency services use that is safe and can be kept clear of crowds for them to get to the incident?

There is clear access for emergency vehicles in both Kay Gardens and the Market

Who will be responsible for crowd control during an incident?

Stewards

If required, how would you evacuate your event? What steps would you take?

All entertainment will stop, an announcement will be made to evacuate in outlining areas.

How will you communicate the evacuation instruction to your audience?

Via the stage PA in the first instance and then via stewards.

Please provide details of any emergency signage that will be used at your event (i.e. emergency exit signs)

The event is outdoor but exit areas will be signposted.

4.	Traffic Management

4.1	Traffic Management

Please answer the following questions in detail regarding traffic management at your event

Is your event taking place on or off the Highway?

Off the Highway

What is the best route for traffic to take in order to get to your event? How will this be communicated?

Traffic can access the event normally and there is no change to the current access.

What is the best and safest route for traffic to exit your event? How will this be communicated?

Traffic can leave the event normally, there is no change to access.

In the interest of pedestrian safety, how will pedestrians interact with vehicle movement? Please include information about how they will cross open roads safely.

There are clear crossings near to the event. All areas are pedestrianised.

What have you done to liaise with and inform local residents and businesses about the impact to local roads?

All businesses have been informed via the BID newsletter.

Can people enter your event without causing an obstruction on the road?

Yes.

How have you considered the impact that your event will have on public transport? Have you informed Transport for Greater Manchester?

Yes, TfGM have been informed.

Are you requesting any parking suspensions as part of your event? If yes, please give details below and contact parking@bury.gov.uk

N/A

If the answer to this is none, please explain why you think there will be no impact on parking, access or traffic flow. As the organiser you are responsible for ensuring there is none/minimal impact to traffic.

Car parking on open market days can cope with increased traffic, following other similar events. On Thursday, carparks are underutilised and unlikely to fill.

4.2	Road Closures

IMPORTANT NOTE: Before a road closure can be considered the following documents MUST be submitted to traffic@bury.gov.uk along with this plan and approved by KCC Highways Authority: - A copy of valid Public Liability Insurance (£5 million minimum) - Health and Safety Risk Assessments - Signage Schedule (Map and indication of where signs will go) - Plan of diversion route (if applicable) Please note Bury Council Highways require 12 weeks’ notice of any road closures for coordination purposes.

Please answer the following questions in detail regarding any road closures at your event

Are you applying for a road closure as part of your event?

No

Please complete the ‘Application Form’ below and send to traffic@bury.gov.uk (refer to guidance notes).

Please provide details of the road closures you will be requesting including timings:

There are no road closures

Who is providing your signage for the road closure? If you are using a signage contractor, please provide their details here. Please ensure you check their public liability insurance. A copy of the signage schedule produced by the contractor must be provided to Bury Council. Please provide a signage schedule and a Health and Safety risk assessment for working on the highway.

N/A

Please confirm arrangements for stewards assisting with the road closures.

N/A

5.	Event Safety Measures

Please provide full details of what control measures will be in place to ensure the safety of members of the public and staff/volunteers at your event in line with current Government guidelines.

All Stewards volunteers will be briefed prior to the event of the items mentioned in this form. Stewards will be in constant communication. All staff and teams are fully aware of emergency response plans. Dynamic RAs will be completed throughout the day in conjunction with RAs. All stalls are required to provide Public liability insurance and any food retailers must have a 5 food hygiene rating. Reviews of safety measures are undertaking prior to the event and communicated to all staff and teams involved. Stall holders and traders are made aware of safety measures and plans in place in the event of an emergency.

Appendices

i.	Site Map

Please provide a site map of your event site

Red Lines signify road closure barriers, entrance, exits and fire escape routes.

ii.	Risk Assessment

Please complete an event specific risk assessment including a fire risk assessment

iii.	Public Liability Insurance

Please provide a copy of your public liability insurance certificate (for a minimum of £5 million) – Covered by Bury Market each stall will have their own Public Liability Insurance

iiii.	Road Closure Documents (if applicable) – NOT APPLICABLE

- A copy of valid Public Liability Insurance (£5 million minimum)

- Health and Safety Risk Assessments including reference to risks on the Highway

- Signage Schedule (Map and indication of where signs will go)

- Plan of diversion route (if applicable)

NEWCASTLE-UNDER-LYME DOCUMENTS

Templates/Risk Assessments

Safety instructions

All Council officers undertaking manual handling must ensure thay
have undertaken corporate Health and Safety awareness training and understand the Risk Assessment associated with this duty.

Online HSE guidance can be found here: Manual handling at work - Musculoskeletal disorders - HSE Newcastle-under-Lyme Borough Council runs in-person and refresher Manual Handling courses.

RiskAssessment_215886.pdf

View

_________________________________________________________________________________________